CRIMSON HORSE

Delivery plan

Exactly what has to happen to make the product usable on a desk and then sellable. Who does each step. How the Calculator and the report stay flexible when the solicitor changes the method.

This plan is an operating document. It is not legal advice. The solicitor instructs the method and the rates. Crimson Horse calculates those instructions correctly, names every assumption, and leaves blank anything that has no source and no instruction.

# 1. The situation we must plan for

There is not one quantum. Counsel and valuers already use different shapes on the same papers. The Carlin How opinion records JDH at 4% on the sums paid and 2% on wholesale, with no delivery uplift. The Centurion opinion records Mersenne as wholesale plus 40%, standing charges, and 8%. You have instructed 6% in place of 8%, and kept 40%. A later solicitor may ask for 4%/2%, or 8% both sides, or commission-only, or actual C and D from a supplier ledger, or bill-by-bill interest instead of a mid-point clock.

If we freeze one method into the product, the next instruction will break it. If we guess a method so a report looks finished, we have failed the hard rule. The product must therefore calculate every instructed method correctly, show them side by side, and let the solicitor say which line is headline.

# 2. Policy — method, rates, and the report

## 2.1 Who decides

| Question | Who decides | What Crimson Horse does |
| --- | --- | --- |
| Whether there is a claim, and how it is pleaded | The solicitor | Does not advise. Does not copy counsel’s prospects into the valuation as a Crimson Horse finding. |
| Headline measure (Wood, fair-cost, commission-only, or another named method) | The solicitor, in a written instruction on the case file | Runs every instructed method. Marks which is headline. Does not hide the others. |
| Interest rate on A (B) and on C+D (E) | The solicitor’s note, or a named sourced report they have adopted | Applies only that. 6%, 8%, 4%/2%, SONIA — none is a default. |
| 40% of wholesale as D, or any other uplift | The solicitor’s note | Applies as a proxy, marked proxy, until actual delivery cost exists. |
| Estimated / imputed bills | The solicitor’s note | Flags the row IMPUTED. Totals never invented without that note. |
| What is a fact on a page | The page | Copied into the Data Bridge with the file named. |

## 2.2 Standing rules (do not relax)

No rate, uplift, wholesale series, or commission p/kWh is invented to fill a gap.

One case, one folder. Mortgage files and AppleDouble ._ files are held out.

A method that cannot run is blank, not zero.

Every assumption is named in the report next to the figure it affects.

Four-eyes before a draft leaves the desk.

The live Calculator is not changed in silence. Weekly review: agree, later date, or reject this week only.

The report is a quantum valuation. It is not legal advice and not an expert report.

## 2.3 Flexibility — what “the solicitor will ask for all sorts” means in practice

The instruction file on the case (instruction.json / solicitor note) must be able to carry, at least:

| Switch | Examples already seen | Product behaviour |
| --- | --- | --- |
| Headline method | Wood A+B−(C+D+E); fair-cost; commission floor | All calculated if the inputs exist; headline labelled from the instruction. |
| B rate | 8% Mersenne; 6% instructed; 4% JDH/Wood claimant leg | Single cell, per case. |
| E rate | Same as B; or 2% Wood supplier leg | Separate cell. Must not be forced equal unless instructed. |
| D / delivery | Bare C only (JDH); 40% of C (Mersenne); actual supplier build-up | Three D modes: none / instructed % of C / actual £. |
| C source | OFGEM average as cited; supplier hedge book; blank | Named. Blank if none. |
| Interest clock | Bill-by-bill to a calculation date; mid-point years (marked assumption) | Bill-by-bill preferred. Mid-point only if instructed and marked. |
| Commission line | Ledger £; instructed %; instructed p/kWh; JDH estimate copied with mark | Never a typical-market guess from us. |
| Imputed months | On / off | Off unless instructed. |

When a new combination arrives, it is not a redesign of the product. It is a new row on the instruction file and, if the Calculator cannot yet do it, a weekly-review item. Live cases stay on the frozen file until “agree” is written.

# 3. Is the Calculator appropriate?

The live file in the library is Crimson_Calculator_v2.10.xlsm (Home, Contracts, Bills, Lists). It was inspected for this plan.

## 3.1 What it already does that we need

Case, sites, MPAN, broker, supplier on Home.

Commission Rate and Stat Int Rate as case-level inputs — the right place for solicitor-instructed rates.

Contracts: signed/start/end, standing charge, day/night (and further periods), EAC, bill rates, Fair Peak / Fair Base, length, quantum and statutory interest columns, overpayment before/after claim date.

Bills: period, kWh, payment, contractual utility cost, rescission payment, claim value, statutory interest, CCL, EBRS, imputed bills in italics.

Lists: utility types, standing-charge bases, CCL by year, brokers, suppliers.

That is a working engine for contracts, bills, a fair-rate overpayment, a rescission column, and one statutory interest rate.

## 3.2 What it does not yet do — and why that matters

| Gap | Why the solicitor will hit it | Required change (weekly review, then freeze) |
| --- | --- | --- |
| One Stat Int Rate only | Wood / JDH use two rates (B on A, E on C or C+D). Mersenne/your instruction use one rate both sides. The file cannot currently hold both 4% and 2% at once, or 6% on A and 2% on C+D. | Add B rate and E rate as separate instructed cells. Default neither. If only one is instructed, the other stays blank unless the instruction says “same as B”. |
| No labelled C and D on a summary | A+B−(C+D+E) is the shape of the Carlin How and Centurion write-ups. Fair Peak/Base is a different door into a similar idea. | Add a Method panel: C (£ or p/kWh source), D mode (none / % of C / actual £), B, E, calculation date. |
| No side-by-side methods | Counsel treat fair-cost, Wood, and commission as different lines. The report must show all instructed lines. | Output three results (or as many as instructed), each marked sourced / proxy / instructed. Headline chosen by the instruction, not by the spreadsheet author. |
| Wholesale series not in the file | JDH used OFGEM averages; Mersenne used wholesale + 40%. Neither series is a sheet in v2.10. | Do not embed a guessed series. Allow C to be pasted from a named source file, or left blank. Adding a published series is a weekly-review agree only. |
| Fair Peak / Fair Base can be typed with no source | That is how a 40% proxy or a “typical” rate could sneak in unmarked. | Fair rates accepted only with a source tag (instruction / named report / blank). Blank means Method fair-cost does not run. |
| Macros stay in the .xlsm | Extract can write values; it must not strip VBA. | Populate cells, keep the workbook. Test after each fill. |

Verdict: v2.10 is the right host for contracts and bills, and it is not yet sufficient for solicitor-led method switching. It is appropriate as the frozen live file for data entry today. It is not appropriate to sell as “the Calculator finishes Wood, fair-cost and commission to instruction” until the Method panel above is built, tested on Carlin How numbers, and frozen.

# 4. What “done” looks like

## 4.1 Usable (your desk)

A complete energy folder in. Intake report, Data Bridge, Calculator, and a Carlin How–style valuation out. Four-eyes signed. Solicitor can instruct a different B, E or D and the same papers re-run without rewriting the product.

## 4.2 Sellable (a buyer’s desk)

The same loop on a second PC, from an installer, with a brand file, without the build team in the room. Screen optional. Limitations written on the tin.

# 5. Who does what, and when

Owner = the person who will sell or run the product. Operator = first desk user. Reviewer = second pair of eyes. Builder = Crimson Horse engineering (this Agent). Solicitor = the instructing solicitor on the live case. JF in the earlier notes is treated as Owner unless you name someone else.

## Phase A — freeze and policy (this week, before another case)

| # | Task | Who | Done when | Library file to use |
| --- | --- | --- | --- | --- |
| A1 | Name owner, operator, reviewer. One machine for v1. | Owner | Names written on the go-live checklist | Go-live checklist; First week on a desk |
| A2 | Adopt this delivery plan and the method policy in section 2. | Owner | This file dated and kept with the live Calculator | This plan; Weekly review; Solicitor-instructed commission and interest |
| A3 | Freeze live files: Calculator v2.10, empty Data Bridge, current valuation template, four-eyes sheet. | Owner + operator | Only those files on the desk | working/; templates/BEC_Hybrid_Quantum_Valuation_Template_v2.docx |
| A4 | Write the instruction template the solicitor will sign: headline method, B, E, D mode, imputed bills yes/no, calculation date. | Builder then Owner | instruction.example.json matches the Word note the solicitor sees | examples/instruction.example.json; Solicitor_Instructed_Commission_and_Interest.docx |
| A5 | Publish or share the library (48+ files). Staff know where it lives. | Owner | URL or zip on the shared drive; sign-in if the site is public | Crimson Horse library; this plan once filed |

## Phase B — Calculator fit for solicitor instructions (before sell, can start in parallel with C)

| # | Task | Who | Done when |
| --- | --- | --- | --- |
| B1 | Add Method panel: B rate, E rate, D mode (none / % of C / actual), C source, calculation date, headline flag. | Builder | Carlin How JDH A £33,269.85 and C £10,639.70 can be typed in and the three lines appear: (i) JDH 4%/2% bare C, (ii) Wood 6%/6% with 40% D, (iii) commission estimate as instructed or blank |
| B2 | Stop fair-rate and commission cells calculating if source tag is empty. | Builder | Blank in, blank out — no zero |
| B3 | Keep imputed-bills flag; only run if instruction says so. | Builder | Matches Missing bills note |
| B4 | Weekly review: agree the Method panel onto the frozen live file. Archive v2.10 as previous live. | Owner | Log line dated; desks on one version |
| B5 | Four-eyes on the Carlin How numbers against the published valuation report. | Reviewer | £24,989.01 (6%, 40%, 6.00 years) and £29,685.72 (JDH) both reproducible, or the difference explained |

## Phase C — one complete live case (this is the critical path)

| # | Task | Who | Done when |
| --- | --- | --- | --- |
| C1 | Put one complete energy case in one folder: contract or welcome, LOA if a broker, consecutive bills. No mortgage. No ._ files. | Owner / lead provider | Intake would list those types; Documents for one case is satisfied |
| C2 | Solicitor instruction on that case (even if “no rates — leave B, E, D blank”). | Solicitor via Owner | Note on the folder |
| C3 | Run Extract. Produce intake report + Data Bridge with blanks listed. | Builder first time; then operator | File count matches; wrong types held out |
| C4 | Human complete only evidenced or instructed cells. | Operator | Every remaining blank has an action, not a guess |
| C5 | Load Bridge into Calculator (manual until auto-fill is tested). | Operator | Three cells spotted to the bills |
| C6 | Draft valuation in the Carlin How hybrid structure: facts, methods, named assumptions, document schedule, blanks. | Builder first time; template thereafter | No invented figures; no prospects % |
| C7 | Four-eyes tick sheet. Draft to solicitor only. | Reviewer | Sheet signed or draft stays |

Usable is true when C7 is done once. Do not start a batch of twenty before C7.

## Phase D — the Agent finishes a case without the builder in the room

| # | Task | Who | Done when |
| --- | --- | --- | --- |
| D1 | Auto-write Bridge → Calculator values without stripping macros. | Builder | Second complete case matches the manual fill |
| D2 | Auto-write the Word valuation from the Bridge + instruction (Carlin How structure). | Builder | Third case: operator runs folder in, draft out, reviewer only checks |
| D3 | Add the supplier layouts those cases actually contain (Pozitive, Engie, BG, etc. as they appear). | Builder | Each new layout is a weekly-review item, then frozen |
| D4 | .msg body parse if those cases need emails. | Builder | Only if the folder contains .msg that hold rates or LOA facts |
| D5 | One-case remains the default. Batch of 20 is a later switch, after D2, with the same fail-safes. | Owner + Builder | Not in v1 unless C7 has been clean on three cases |

## Phase E — sellable

| # | Task | Who | Done when |
| --- | --- | --- | --- |
| E1 | Installer: Calculator, templates, Extract, brand file, instruction file, this plan, four-eyes, weekly log. | Builder | A second PC produces a draft from a sample pack |
| E2 | Brand file per buyer (name, colours). Passwords if requested — friction, not uncopyable. | Owner + Builder | Rebranding note is the script |
| E3 | Screen as a separate small tool (yes/no + gap list; figure only if rates are on the page). | Builder if v1 includes it; else later | Lead provider can run it in minutes |
| E4 | Fix a price (seat / pod / Screen / white-label). Pricing_Suggestions.docx is not an offer until you pick numbers. | Owner | Written quote |
| E5 | Limitations page in every sale: not legal advice; solicitor instructs method; blanks stay blank. | Owner | In the pack the buyer signs |
| E6 | Support owner named (who answers “this bill layout failed”). | Owner | A mailbox, not a void |

# 6. The report — what must always be in it

Use the current hybrid template and the Carlin How valuation as the pattern.

What this document is (quantum valuation; not advice).

Parties, contracts, meter — from the pages.

What the papers say about commission — quoted, not argued.

Every instructed method in tables, each marked sourced / proxy / instructed.

Headline method only if the solicitor named it.

Section that lists every assumption (40%, 6%, mid-point years, partial bills, OFGEM C, and any new one).

Document schedule: used for / not used for.

Blanks and required action.

JDH / Mersenne / other third-party totals only as cross-checks, never silently mixed.

Empty appendices not issued.

If the solicitor asks for a new line tomorrow, add a table and an assumption row. Do not rewrite history on last week’s draft; issue a dated revision.

# 7. Library — source of truth

Do not write a second set of rules. These files already hold the pieces. This plan only sequences them.

| Need | File in the library |
| --- | --- |
| What the product is | What the finished product is; PRODUCT_AND_READINESS.md |
| One-case rule and documents to ask for | How one-case mode works; Documents for one case; Lead provider engagement note |
| Rates and imputed bills | Solicitor-instructed commission and interest; Missing bills; instruction.example.json |
| Calculator change control | The weekly review |
| Quality gate | Four-eyes tick sheet; Go-live checklist; What stops a bad number |
| Report pattern | Quantum valuation — Carlin How; Hybrid template v2 |
| Method notes | Wood method note — Carlin How; Wood method note — Centurion Blast |
| Desk week one | First week on a desk; Next steps to launch |
| Commercial / Screen / brand | Commercial and operating pack; Crimson Horse screen; Rebranding, passwords and copying; Pricing suggestions |
| Working files | Crimson_Calculator_v2.10.xlsm; Data Bridge templates; Extract README |

# 8. Sequence on a wall

A1–A5 freeze and policy → C1 folder in (do not wait for B to be perfect) → C3–C7 first draft → B1–B5 Method panel agreed onto the live Calculator → D1–D2 folder-in draft-out → E1–E6 only after three clean cases.

If the folder (C1) is late, B can still proceed using Carlin How’s published A and C as the test pack. Do not test the Method panel on invented kWh.

# 9. What is not in v1

Twenty cases in one pile.

A default 40%, 6%, 8%, or 3p/kWh for buyers who have not instructed them.

Mortgage quantum inside this energy product.

A promise that Screen is a claim value.

Uncopyable files. Passwords only slow a copier down.

# 10. Immediate next actions (do these, in this order)

| Order | Who | Action |
| --- | --- | --- |
| 1 | Owner | Confirm operator, reviewer, and that this plan is the operating document. |
| 2 | Owner | Send one complete energy folder, or confirm Carlin How remains the test pack until that folder exists. |
| 3 | Solicitor via Owner | Return the instruction template: headline method; B; E; D mode; imputed bills; calculation date. “Leave blank” is a valid instruction. |
| 4 | Builder | Build the Method panel on a dated copy of the Calculator (not silent overwrite of v2.10). Prove Carlin How two-line output. |
| 5 | Owner | Weekly review: agree or reject that copy. Only then does it become live. |
| 6 | Builder + operator + reviewer | Run C3–C7 on the first complete folder (or re-run Carlin How as the dry run). |
| 7 | Owner | Do not sell until D2 has worked on a case the builder did not hand-write. |

The product is deliverable. The risk is not missing notes — they are in the library. The risk is freezing one method, or selling before the Calculator can switch methods on instruction. This plan exists so neither happens.